## ProjectSchedule
Flood-Prediction-Using-WeatherAPI-and-historical-thread-mapping
TIET Patiala - UCS503 Software Engineering |  | Project Start: | 2026-08-03
Project Lead: Amit Bishnoi (Roll No: 1024240005) |  | Today: | 2026-09-13
|  | Display Week: | 1 |  |  | 2026-08-03 | [6 empty] | 2026-08-10 | [6 empty] | 2026-08-17 | [6 empty] | 2026-08-24 | [6 empty] | 2026-08-31 | [6 empty] | 2026-09-07 | [6 empty] | 2026-09-14 | [6 empty] | 2026-09-21
 | time axis 2026-08-03 to 2026-09-27
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2026-08-03 to 2026-09-27
Phase 1: Inception, Planning & Documentation
Project Conception & Scoping | Amit Bishnoi | 100% | 2026-08-03 | 2026-08-08 | 6
Core idea of fusing live meteorological data with historical disaster records | Amit & Diksha | 100% | 2026-08-03 | 2026-08-11
Team Roles & Repository Initialization | Amit & Diksha | 100% | 2026-08-07 | 2026-08-13 | 7
MkDocs & GitHub Pages Configuration | Amit Bishnoi | 100% | 2026-08-10 | 2026-08-15 | 6
Phase 2: System Architecture & Technical Design
Academic Proposal Drafting (LaTeX) | Diksha Garg | 100% | 2026-08-10 | 2026-08-15 | 6
Pitch Slide Deck Design | Diksha Garg | 100% | 2026-08-11 | 2026-08-13 | 3
UML Use Case Design | Amit Bishnoi | 100% | 2026-08-12 | 2026-08-13
Data Flow Diagram (DFD) Modeling | Diksha Garg | 100% | 2026-08-14 | 2026-08-15
Entity-Relationship (ER) Architecture | Diksha Garg | 100% | 2026-09-07 | 2026-09-08
Activity Diagram | Amit Bishnoi | 100% | 2026-09-09 | 2026-09-10
Phase 3: Data Engineering & Spatial Prototyping
Historical Data Ingestion & Collection | Amit Bishnoi | 100% | 2026-08-12 | 2026-08-15 | 4
Data Cleaning & Standardization | Diksha Garg | 100% | 2026-08-16 | 2026-08-19 | 4
Dataset Merging (Fused Database) | Diksha Garg | 100% | 2026-08-19 | 2026-08-21 | 3
Spatial Indexing & Haversine Math | Diksha Garg | 100% | 2026-08-22 | 2026-08-25 | 4
Phase 4: Machine Learning & Backend Development
Feature Engineering Pipeline | Amit Bishnoi | 80% | 2026-08-27 | 2026-08-28 | 2
Machine Learning Model Training | Amit Bishnoi | 80% | 2026-08-30 | 2026-09-03 | 5
Synthetic Overlapping Data Generation | Amit Bishnoi | 50% | 2026-09-14 | 2026-09-21 | 8
Flask Server & API Routing | Amit Bishnoi | 100% | 2026-09-05 | 2026-09-07 | 3
Mock Weather Fallback System | Amit Bishnoi | 40% | 2026-10-07 | 2026-10-13 | 7
Phase 5: Frontend Integration & Final Documentation
Frontend UI Dashboard Layout | Amit Bishnoi | 60% | 2026-08-13 | 2026-08-15 | 3
Leaflet.js Mapping Integration | Amit & Diksha | 80% | 2026-09-03 | 2026-09-05 | 3
Gantt Chart Milestone Planning | Diksha Garg | 90% | 2026-09-09 | 2026-09-09 | 1
Progress Journal Authoring | Amit & Diksha | 100% | 2026-08-03 | 2026-09-13 | 42
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.